## Sheet1
2017-10-16
|  | # | Task | BA | Comment
|  | 1 | SQL Pull w/ Computation | Tac/Mike | For testing tomorrow
|  | 2 | Data Cleansing | Tof - (Junie/Basti) | Not yet started due to Mark Collins report prioritization ¦ will already be included on Mike’s SQL pull
|  | 3 | File Splitter | Tof | Already prepared draft, waiting for the final commissions data with column headers
|  | 4 | Sending Email with Attachment | Glen | Currently creating code for attachment of email, change library
|  | 5 | Weekly update of tables | Tac/Mike | Will start tomorrow
|  |  | 2017-10-17 | 17:00
|  | # | Task | BA | Comment
|  | 1 | SQL Pull w/ Computation | Tac/Mike | Pull raw data to be sent to mike for the sql computation
|  | 2 | Data Cleansing | Tof - (Junie/Basti) | Already done via SQL with Mike, tof to receive the final output
|  | 3 | File Splitter | Tof | will split the file per broker and paste using Mark Collins Format
|  | 4 | Sending Email with Attachment | Glen | script ongoing on attach email per type,
|  | 5 | Weekly update of tables | Tac/Mike | Will do after the computation
2017-10-17 |  |  | 2017-10-17 | 19:00
|  | # | Task | BA | Comment
|  | 1 | SQL Pull w/ Computation | Tac/Mike | Combining Tac Query and Mike Query, Stored Procedure is already created, for testing once Mercury is Up.
|  | 2 | Data Cleansing | Tof - (Junie/Basti) | Done
|  | 3 | File Splitter | Tof | Still creating Mark Collins report, will proceed once done.
|  | 4 | Sending Email with Attachment | Glen | Serial Number Creation
|  | 5 | Weekly update of tables | Tac/Mike | After SQL Pull Computation
|  |  | 2017-10-18 | 19:00
|  | # | Task | BA | Comment
|  | 1 | SQL Pull w/ Computation | Tac/Mike | Joining MTM deals, getting broker details from expansion deals, incorporating serial number on all tables, Completed: Stored Procedures, joining tac query to mike query
|  | 2 | File Splitter | Tof | Already working, waiting for new data set with serial number
|  | 3 | Sending Email with Attachment | Glen | Completed, waiting for sql query and adding picture on the signature
|  | 4 | Weekly update of tables | Tac/Mike | Will pursue once task number 1 is completed
|  | 5 | Moving Emails/Matching data with 4 parameters and sending to DB for Exact Matches | Junie/Basti | Moving and Matching is done, waiting for the final columns set on Mike's table to complete the calculation for us to set the formulas